## Audit Followup
No | SQID Ref. | Finding | Requirement-references | Operator Comments | Class | Priority | Target closure date | Resp. | Status CHC HS | Status Joint Audit | Joint Audit Comment | Joint Audit Adjusted closure date
5.1.1 | 9709 | Responsibilities concerning the ERP (overall responsibility, responsibility for the manual, for the practical execution of exercises etc.) should be clearly stated in the manuals, or one of the manuals. (ref: the ERP and SC&M Manuals) | ERP and SCM Manual | Overall responsibility and the practical responsibility is implemented in both the new SMM and in a revised ERP manual. Ref. ERP Manual chapter 0 | Finding | M | 2020-10-01 | S&Q | Open | Closed
5.1.2 | 9710 | An overall analysis of the data derived from the internal and external audits should be undertaken in order to assess the suitability and efficiency of the Quality (Safety & Compliance) monitoring system and function. | ISO 9001:2015 | There is an evaluation made in the annual report FY 2020 in relation to the Quality monitoring system. In the monthly ORB's adits are adressed and issues discussed as a specified part of the meeting. | Finding | M | 2020-10-01 | S&Q | Follow up | Closed
5.1.3 | 9711 | The HESS Advisors responsibilities concerning security should be stated in the HESS Manual. | CHC HS HESS manual | Implemented in the manual ref. ERP Manual chapter 4.3 | Finding | L | 2020-10-01 | S&Q | Follow up | Closed
5.1.4 | 9712 | A contract stating the relation between Securitas and CHC HS could not be presented during the audit. | EASA ORO.GEN 205 | This was a misunderstanding, contract is available. Contract enclosed appendix xx | Finding | M | 2020-10-01 | Ground Ops | Open | Closed
5.1.5 | 9713 | The completed MoC concerning the Ground Operations restructure (outsourcing) could not be presented in the audit. | ERP and SCM Manual | MOC was performed and has SQID number MOC-000304 | Finding | L | 2020-10-01 | Management | Follow up | Closed
5.1.6 | 9714 | The management of risk is described in different processes. It is hard to see from the SC&M Manual how these different risk management descriptions come together in the risk register and the current bow tie, given those are the two ultimate (or penultimate) expressions of the current risk picture in the company. In sum it may be difficult to secure that all risks are manged as intended in ORO.GEN 200. | EASA ORO.GEN 200 | New manual based on a global standard is to be issued medio mid November pending capacity in CAA-N. The SMM will give a more clear description of Risk management process. The final version is sent to CAA-NO for approval with a tentative publication of 01 March 21.Chapter 2 discribes Risk Management. See attached manual. | Finding | M | 2020-10-01 | S&Q | Open | Open | Pending additional feed back. New closing date 15.02.2021 | 2021-02-15
5.2.1 | 9715 | We register that the climate for cooperation between CHC HS and Bristow is good. However, there is something to be desired concerning the timely sharing of information between the companies in the cases of serious events. We suggest the companies look into this for the purpose of improving non-competitive information sharing. |  | We have had a coordination meeting between CHC HS and Bristow with AM and S&C managers. We have agreed on quaterly meetings combined with Heliapp coordination meeting. These meeting will be held up front of HSCN meetings. CHC HS has also implemented i DSRM to evaluate information to Operators. Also part of the Investigation process and ERP process. | Obs |  | 2020-10-01 | S&Q | Open | Closed | To be checked Common Audit 2021.
5.2.2 | 9716 | The yearly performance review had not been completed for all technicians at some of the bases. |  | All responsible leaders have an action item with due date end year to perform yearly performance review. Plan for performance review is in SQID but not completed due ongoing training for some of the personnel prforming the review. Se vedlagt bilde av action i SQID | Obs |  | 2020-10-01 | Part 145 | Follow up | Open | New closing date 15.02.2021 | 2021-02-15
5.2.3 | 9717 | The CHC MOE does not mention any training requirement for the handling of parts in relation to ESD (Electrostatic Discharge). |  |  | Obs |  | 2020-10-01 | Part 145 | Follow up | Closed
5.2.4 | 9718 | The NP Part M will revert back to the Common Audit on why there is a sudden dip in MEL statistics for May. We also observe an increase in MEL use before May, but none of the other relevant KPIs (robberies, MDR) indicate anything in particular pointing to any problems related to the lack of parts. |  | MEL trending analysed. Part-M manager will give a breifing | Obs |  | 2020-10-01 | Part M | Open | Closed | Breifing received and closing accepted.
5.2.5 | 9719 | In different MoM from different FDM meetings it is hard to see concrete actions and also whether the different outputs are being tracked in the management (SQID) system. |  | Will be documented in SQID(Most likely Meetings Module) Decision to use One Note see attached picture of the module. | Obs |  | 2020-10-01 | Flight Ops | Open | Open | Introduction of use of the SQID meeting module must be verified. New closing date 15.02.2021. | 2021-02-15